**Example Poster for Implementation Workshop**

*Supports Step 3.3: Develop an implementation pathway and performance tracking. Use the template and delete content that you do not plan to use.*

**Example Poster for Implementation Table**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Strategy  or Project** | **Implementation Lead + Support** | **Implementation Timeline** | **Estimated  Cost and Other Resources Needed** | **Possible Resources** | **Direction Check** |
| *Include resilience as part of capital improvement scoring process* | *Budget & Management (Andre Williams, Director)* | *Research models and provide report to council and mayor*  *Pilot prioritization process*  *Assess progress and success* | *Support from Council*  *Staff time to research and write language*  *Training or guidance needed for staff?*  *Staff time to capture progress and outcomes* | *Planning staff, summer intern* | *More funded projects consider hazard mitigation  or resilience* |
| *Conduct an assessment and map drainage ditches and other stormwater conveyance systems.* | *Public Works (Susan Harrell, Director)* | *Draft scope  of work*  *Retain consultant*  *Engage the community*  *Complete assessment  and mapping* | *Council approval*  *Staff time to retain consultant, prepare scope, orient the consultant to the project/community*  *Cost of assessment and mapping- Approximately $150,000* | *DEQ grant*  *Non-profit partner will assist with community engagement* | *Completed assessment  and mapping* |